## Timeline
Name of Event: | [5 empty] | How to Use This Tool:
Enter Date of Event: |  | 2020-03-01
(if multiple event dates, enter the earliest date) | [5 empty] | 1. Enter the name of your event.
2. Enter the date of your event.
3. Be sure to use the 'Enter' key after adding the date.
4. Watch the timeline magically adjust to your date.
Event Phases
Start | End | # of Days | Label | Vert. Position | Vert. Line
2020-01-05 | 2020-01-25 | 21 | Conceptualization Phase | -50 | -50
2020-01-15 | 2020-01-28 | 14 | Approvals Phase | -60 | -10
2020-01-29 | 2020-03-01 | 32 | Promotions Phase | -70 | -10
2020-02-04 | 2020-03-08 | 34 | Logistics Phase | -80 | -10
Milestones
Date |  |  | Label | Position
2020-01-05 |  |  | Start, Jan 5 | 30
2020-01-12 |  |  | Risk Assessed | 13
2020-01-17 |  |  | Budget Approved | -30
2020-01-17 |  |  | Space Reserved | 40
2020-01-19 |  |  | PC Request done | 22
2020-02-04 |  |  | Ensure Event Accessibility | 15
2020-02-06 |  |  | Finalize Food Plan / Catering | -35
2020-02-09 |  |  | Contracting done | -55
2020-02-09 |  |  | Start Promo on WIN & Social Media | 40
2020-02-14 |  |  | Finalize Staffing & Space Needs | 25
2020-02-16 |  |  | Posters/Banners up | 7
2020-02-16 |  |  | All ER's done | -40
2020-03-01 |  |  | Event Date, Mar 1 | 30
2020-03-03 |  |  | Thank You's & Assessment | -40
Formulas:
Start = [End, row above]-10
Start = [End, row above]+1
End = [Start]+D35-1
Note on E45: Get "greenlight" from your advisor or VU staff that this event is do-able
Note on E48: PC: Publicity Center
Note on E55: ER: Expenditure Request